## Project Plan
Project ID | PRJ-1108 | WBS | Phase | Task ID | Project Activity | Owner | Team | Status | % Complete | Priority | Critical path (Yes/No) | Dependency (If any / Predecessors) | Risk Level (Low / Medium / High / Critical) | Planned Start Date | Actual Start Date | Planned Finish Date | Actual Finish date
Project Name | Helios Data Platform | 1 | Initiation | 1.1 | Project Charter | C. Meyer | Security | Complete | 100 | High | Yes |  | Low | 2026-03-02 | 2026-03-01 | 2026-03-10 | 2026-03-12
|  |  |  | 1.2 | Initiation Meeting SP Tech Internal | A. Silva | Platform | Complete | 100 | Medium | No |  | Low | 2026-03-07 | 2026-03-10 | 2026-03-16 | 2026-03-21
Planned Go Live Date | 2026-10-10 |  |  | 1.3 | Initiation Meeting W Vendors | E. Novak | Security | Complete | 100 | High | No |  | High | 2026-03-12 | 2026-03-15 | 2026-03-21 | 2026-03-29
Forcast Go Live Date | 2026-11-07 |  |  | 1.4 | Stakeholder Identification | P. Ahmed | Data | Complete | 100 | Medium | No |  | Low | 2026-03-18 | 2026-03-17 | 2026-03-26 | 2026-04-03
|  |  |  | 1.5 | Internal & External Meeting Cadence Setup | T. Bauer | Security | Complete | 100 | Low | No |  | Low | 2026-03-23 | 2026-03-25 | 2026-04-01 | 2026-04-08
Project Owner | M. Rossi | 2 | Requirements | 2.6 | Project Kickoff Meeting | F. Lindqvist | QA | Complete | 100 | Medium | No |  | Low | 2026-03-29 | 2026-03-29 | 2026-04-06 | 2026-04-18
Business Stakeholder | Enterprise Data Office |  |  | 2.7 | Identify Stakeholders | K. Nair | QA | Complete | 100 | High | No |  | High | 2026-04-03 | 2026-04-06 | 2026-04-12 | 2026-04-23
Project Manager | K. Nair |  |  | 2.8 | Gather Business Requirements | C. Meyer | Data | Complete | 100 | Medium | No |  | Medium | 2026-04-09 | 2026-04-09 | 2026-04-17 | 2026-04-29
|  |  |  | 2.9 | Prepare Business Requirements Document (BRD) | A. Silva | Data | Complete | 100 | Low | No |  | Low | 2026-04-14 | 2026-04-16 | 2026-04-23 | 2026-05-14
|  |  |  | 2.1 | Requirements Sign-Off | E. Novak | QA | Complete | 100 | High | Yes |  | Low | 2026-04-20 | 2026-04-22 | 2026-04-28 | 2026-05-14
|  | 3 | Design | 3.2 | Solution Design Workshop- SP Tech Internal | P. Ahmed | QA | Blocked | 29 | High | No |  | Critical | 2026-04-25 | 2026-04-25 | 2026-05-04
|  |  |  | 3.3 | Solution Design Workshop- W Vendors | T. Bauer | Data | Blocked | 25 | Low | No |  | Low | 2026-05-01 | 2026-05-02 | 2026-05-09
|  |  |  | 3.4 | Prepare Functional Requirements Document (FRD) | F. Lindqvist | QA | In Progress | 47 | Low | No |  | Low | 2026-05-06 | 2026-05-06 | 2026-05-15
|  |  |  | 3.5 | Process Flow Design | K. Nair | Data | Not Started | 0 | Medium | No |  | Low | 2026-05-12 |  | 2026-05-20
|  |  |  | 3.6 | Technical Architecture Review | C. Meyer | QA | Not Started | 0 | High | Yes |  | Low | 2026-05-17 |  | 2026-05-26
|  |  |  | 3.7 | Security & Compliance Review W Security Team | A. Silva | Data | Not Started | 0 | Medium | No |  | Low | 2026-05-22 |  | 2026-05-31
|  |  |  | 3.8 | Integration Design | E. Novak | Security | Not Started | 0 | Low | No |  | Low | 2026-05-28 |  | 2026-06-05
|  | 4 | Development | 4.9 | Environment Setup | P. Ahmed | Data | Not Started | 0 | Low | No |  | Medium | 2026-06-02 |  | 2026-06-11
|  |  |  | 4.1 | Configuration Activities | T. Bauer | Security | Not Started | 0 | Medium | No |  | Low | 2026-06-08 |  | 2026-06-16
|  |  |  | 4.2 | Custom Development (If any) | F. Lindqvist | Data | Not Started | 0 | Low | No |  | Low | 2026-06-13 |  | 2026-06-22
|  |  |  | 4.3 | Integration Development | K. Nair | QA | Not Started | 0 | Medium | No |  | Low | 2026-06-19 |  | 2026-06-27
|  |  |  | 4.4 | Unit Testing | C. Meyer | Security | Not Started | 0 | Medium | No |  | Low | 2026-06-24 |  | 2026-07-03
|  | 5 | Testing | 5.5 | Test Plan Preparation | A. Silva | QA | Not Started | 0 | Low | No |  | Low | 2026-06-30 |  | 2026-07-08
|  |  |  | 5.6 | Testing Steps & Scenarios | E. Novak | Security | Not Started | 0 | Medium | No |  | Low | 2026-07-05 |  | 2026-07-14
|  |  |  | 5.7 | System Testing (SIT) | P. Ahmed | Data | Not Started | 0 | Low | No |  | Low | 2026-07-11 |  | 2026-07-19
|  |  |  | 5.8 | Integration Testing | T. Bauer | QA | Not Started | 0 | Medium | No |  | Low | 2026-07-16 |  | 2026-07-25
|  |  |  | 5.9 | QA | F. Lindqvist | Data | Not Started | 0 | Medium | No |  | Low | 2026-07-22 |  | 2026-07-30
|  |  |  | 5.1 | User Acceptance Testing (UAT) | K. Nair | QA | Not Started | 0 | High | Yes |  | Low | 2026-07-27 |  | 2026-08-05
|  |  |  | 5.2 | UAT Sign Off by Business | C. Meyer | QA | Not Started | 0 | High | Yes |  | Critical | 2026-08-02 |  | 2026-08-10
|  | 6 | Implementation | 6.3 | User Training / Demo | A. Silva | Security | Not Started | 0 | Medium | No |  | Low | 2026-08-07 |  | 2026-08-16
|  |  |  | 6.4 | User Training | E. Novak | Data | Not Started | 0 | Medium | No |  | Low | 2026-08-12 |  | 2026-08-21
|  |  |  | 6.5 | Cutover Planning | P. Ahmed | QA | Not Started | 0 | High | Yes |  | Low | 2026-08-18 |  | 2026-08-26
|  |  |  | 6.6 | Go-Live Readiness Review | T. Bauer | Platform | Not Started | 0 | High | Yes |  | Low | 2026-08-23 |  | 2026-09-01
|  |  |  | 6.7 | GO NO GO Discussion / Approval | F. Lindqvist | QA | Not Started | 0 | High | Yes |  | Medium | 2026-08-29 |  | 2026-09-06
|  | 7 | Go Live | 7.8 | Production Deployment | K. Nair | Platform | Not Started | 0 | High | Yes |  | High | 2026-09-03 |  | 2026-09-12
|  |  |  | 7.9 | Hypercare Support | C. Meyer | Platform | Not Started | 0 | High | No |  | High | 2026-09-09 |  | 2026-09-17
|  |  |  | 7.1 | Lessons Learnt | A. Silva | Security | Not Started | 0 | Medium | No |  | Low | 2026-09-14 |  | 2026-09-23
|  |  |  | 7.2 | Project Closure | E. Novak | QA | Not Started | 0 | Low | No |  | Medium | 2026-09-20 |  | 2026-09-28
|  |  |  | 7.3 | Post Go Live Support ¦ 4 weeks | P. Ahmed | QA | Not Started | 0 | Low | No |  | Medium | 2026-09-25 |  | 2026-10-04