## Project Plan
Project ID | PRJ-1077 | WBS | Phase | Task ID | Project Activity | Owner | Team | Status | % Complete | Priority | Critical path (Yes/No) | Dependency (If any / Predecessors) | Risk Level (Low / Medium / High / Critical) | Planned Start Date | Actual Start Date | Planned Finish Date | Actual Finish date
Project Name | Orion CRM Rollout | 1 | Initiation | 1.1 | Project Charter | P. Ahmed | Apps | Complete | 100 | High | Yes |  | Low | 2026-01-12 | 2026-01-11 | 2026-01-20 | 2026-01-21
|  |  |  | 1.2 | Initiation Meeting SP Tech Internal | V. Rao | Integration | Complete | 100 | Medium | No |  | Low | 2026-01-17 | 2026-01-18 | 2026-01-25 | 2026-01-27
Planned Go Live Date | 2026-08-20 |  |  | 1.3 | Initiation Meeting W Vendors | T. Bauer | QA | Complete | 100 | High | No |  | High | 2026-01-22 | 2026-01-24 | 2026-01-31 | 2026-02-02
Forcast Go Live Date | 2026-09-01 |  |  | 1.4 | Stakeholder Identification | F. Lindqvist | Apps | Complete | 100 | Medium | No |  | Medium | 2026-01-28 | 2026-01-27 | 2026-02-05 | 2026-02-08
|  |  |  | 1.5 | Internal & External Meeting Cadence Setup | H. Costa | QA | Complete | 100 | Medium | No |  | Low | 2026-02-02 | 2026-02-04 | 2026-02-11 | 2026-02-13
Project Owner | S. Adeyemi | 2 | Requirements | 2.6 | Project Kickoff Meeting | N. Kaur | Integration | Complete | 100 | Medium | No |  | Low | 2026-02-08 | 2026-02-08 | 2026-02-16 | 2026-02-21
Business Stakeholder | Commercial Sales |  |  | 2.7 | Identify Stakeholders | L. Zhou | Integration | Complete | 100 | Low | No |  | Low | 2026-02-13 | 2026-02-15 | 2026-02-21 | 2026-02-24
Project Manager | L. Zhou |  |  | 2.8 | Gather Business Requirements | P. Ahmed | Integration | Complete | 100 | Low | No |  | Low | 2026-02-18 | 2026-02-21 | 2026-02-27 | 2026-03-05
|  |  |  | 2.9 | Prepare Business Requirements Document (BRD) | V. Rao | PMO | Complete | 100 | Medium | No |  | Low | 2026-02-24 | 2026-02-27 | 2026-03-04 | 2026-03-07
|  |  |  | 2.1 | Requirements Sign-Off | T. Bauer | PMO | Complete | 100 | High | Yes |  | Low | 2026-03-01 | 2026-03-04 | 2026-03-10 | 2026-03-16
|  | 3 | Design | 3.2 | Solution Design Workshop- SP Tech Internal | F. Lindqvist | Apps | Complete | 100 | Low | No |  | Low | 2026-03-07 | 2026-03-06 | 2026-03-15 | 2026-03-21
|  |  |  | 3.3 | Solution Design Workshop- W Vendors | H. Costa | PMO | Complete | 100 | Low | No |  | Medium | 2026-03-12 | 2026-03-13 | 2026-03-21 | 2026-03-25
|  |  |  | 3.4 | Prepare Functional Requirements Document (FRD) | N. Kaur | QA | Complete | 100 | Medium | No |  | Low | 2026-03-17 | 2026-03-18 | 2026-03-26 | 2026-04-02
|  |  |  | 3.5 | Process Flow Design | L. Zhou | Integration | Complete | 100 | Medium | No |  | Low | 2026-03-23 | 2026-03-22 | 2026-03-31 | 2026-04-10
|  |  |  | 3.6 | Technical Architecture Review | P. Ahmed | PMO | Complete | 100 | High | Yes |  | Medium | 2026-03-28 | 2026-03-31 | 2026-04-06 | 2026-04-12
|  |  |  | 3.7 | Security & Compliance Review W Security Team | V. Rao | PMO | Complete | 100 | Medium | No |  | Low | 2026-04-03 | 2026-04-05 | 2026-04-11 | 2026-04-18
|  |  |  | 3.8 | Integration Design | T. Bauer | Integration | Blocked | 27 | Medium | No |  | Low | 2026-04-08 | 2026-04-09 | 2026-04-17
|  | 4 | Development | 4.9 | Environment Setup | F. Lindqvist | Apps | Complete | 100 | Medium | No |  | Medium | 2026-04-14 | 2026-04-16 | 2026-04-22 | 2026-04-29
|  |  |  | 4.1 | Configuration Activities | H. Costa | PMO | In Progress | 61 | Low | No |  | Low | 2026-04-19 | 2026-04-21 | 2026-04-27
|  |  |  | 4.2 | Custom Development (If any) | N. Kaur | PMO | Not Started | 0 | Low | No |  | Low | 2026-04-24 |  | 2026-05-03
|  |  |  | 4.3 | Integration Development | L. Zhou | Apps | Not Started | 0 | Medium | No |  | Low | 2026-04-30 |  | 2026-05-08
|  |  |  | 4.4 | Unit Testing | P. Ahmed | QA | Not Started | 0 | Medium | No |  | Low | 2026-05-05 |  | 2026-05-14
|  | 5 | Testing | 5.5 | Test Plan Preparation | V. Rao | QA | Not Started | 0 | Medium | No |  | Low | 2026-05-11 |  | 2026-05-19
|  |  |  | 5.6 | Testing Steps & Scenarios | T. Bauer | Integration | Not Started | 0 | Medium | No |  | Low | 2026-05-16 |  | 2026-05-25
|  |  |  | 5.7 | System Testing (SIT) | F. Lindqvist | Integration | Not Started | 0 | Low | No |  | Low | 2026-05-21 |  | 2026-05-30
|  |  |  | 5.8 | Integration Testing | H. Costa | PMO | Not Started | 0 | Low | No |  | Low | 2026-05-27 |  | 2026-06-04
|  |  |  | 5.9 | QA | N. Kaur | Apps | Not Started | 0 | Low | No |  | Low | 2026-06-01 |  | 2026-06-10
|  |  |  | 5.1 | User Acceptance Testing (UAT) | L. Zhou | PMO | Not Started | 0 | High | Yes |  | High | 2026-06-07 |  | 2026-06-15
|  |  |  | 5.2 | UAT Sign Off by Business | P. Ahmed | QA | Not Started | 0 | High | Yes |  | Low | 2026-06-12 |  | 2026-06-21
|  | 6 | Implementation | 6.3 | User Training / Demo | V. Rao | QA | Not Started | 0 | Medium | No |  | Low | 2026-06-18 |  | 2026-06-26
|  |  |  | 6.4 | User Training | T. Bauer | QA | Not Started | 0 | Medium | No |  | Low | 2026-06-23 |  | 2026-07-01
|  |  |  | 6.5 | Cutover Planning | F. Lindqvist | PMO | Not Started | 0 | High | Yes |  | Low | 2026-06-28 |  | 2026-07-07
|  |  |  | 6.6 | Go-Live Readiness Review | H. Costa | Integration | Not Started | 0 | High | Yes |  | Low | 2026-07-04 |  | 2026-07-12
|  |  |  | 6.7 | GO NO GO Discussion / Approval | N. Kaur | Apps | Not Started | 0 | High | Yes |  | Low | 2026-07-09 |  | 2026-07-18
|  | 7 | Go Live | 7.8 | Production Deployment | L. Zhou | QA | Not Started | 0 | High | Yes |  | Medium | 2026-07-15 |  | 2026-07-23
|  |  |  | 7.9 | Hypercare Support | P. Ahmed | QA | Not Started | 0 | Medium | No |  | Low | 2026-07-20 |  | 2026-07-29
|  |  |  | 7.1 | Lessons Learnt | V. Rao | QA | Not Started | 0 | High | No |  | High | 2026-07-25 |  | 2026-08-03
|  |  |  | 7.2 | Project Closure | T. Bauer | Integration | Not Started | 0 | Medium | No |  | Low | 2026-07-31 |  | 2026-08-08
|  |  |  | 7.3 | Post Go Live Support ¦ 4 weeks | F. Lindqvist | Integration | Not Started | 0 | Low | No |  | Low | 2026-08-05 |  | 2026-08-14