## Project Plan
Project ID | PRJ-1042 | WBS | Phase | Task ID | Project Activity | Owner | Team | Status | % Complete | Priority | Critical path (Yes/No) | Dependency (If any / Predecessors) | Risk Level (Low / Medium / High / Critical) | Planned Start Date | Actual Start Date | Planned Finish Date | Actual Finish date | Effort (hours) | Effort completed (hours) | Effort remaining (hours)
Project Name | Atlas ERP Migration | 1 | Initiation | 1.1 | Project Charter | C. Meyer | Integration | Complete | 100 | High | Yes |  | Low | 2026-02-02 | 2026-02-02 | 2026-02-10 | 2026-02-10 | 84 | 84 | 0
|  |  |  | 1.2 | Initiation Meeting SP Tech Internal | P. Ahmed | Apps | Complete | 100 | Medium | No |  | Low | 2026-02-07 | 2026-02-09 | 2026-02-16 | 2026-02-16 | 16 | 16 | 0
Planned Go Live Date | 2026-09-15 |  |  | 1.3 | Initiation Meeting W Vendors | J. Park | Platform | Complete | 100 | Low | No |  | Low | 2026-02-13 | 2026-02-13 | 2026-02-21 | 2026-02-21 | 80 | 80 | 0
Forcast Go Live Date | 2026-09-15 |  |  | 1.4 | Stakeholder Identification | T. Bauer | Platform | Complete | 100 | Low | No |  | Low | 2026-02-18 | 2026-02-19 | 2026-02-27 | 2026-02-27 | 24 | 24 | 0
|  |  |  | 1.5 | Internal & External Meeting Cadence Setup | A. Silva | Platform | Complete | 100 | Medium | No |  | Low | 2026-02-24 | 2026-02-26 | 2026-03-04 | 2026-03-04 | 60 | 60 | 0
Project Owner | D. Whitfield | 2 | Requirements | 2.6 | Project Kickoff Meeting | V. Rao | Integration | Complete | 100 | Medium | No |  | Low | 2026-03-01 | 2026-03-04 | 2026-03-10 | 2026-03-10 | 24 | 24 | 0
Business Stakeholder | Finance Transformation |  |  | 2.7 | Identify Stakeholders | R. Mendes | Integration | Complete | 100 | Low | No |  | Low | 2026-03-07 | 2026-03-08 | 2026-03-15 | 2026-03-15 | 32 | 32 | 0
Project Manager | R. Mendes |  |  | 2.8 | Gather Business Requirements | C. Meyer | Platform | Complete | 100 | Medium | No |  | Low | 2026-03-12 | 2026-03-13 | 2026-03-21 | 2026-03-21 | 16 | 16 | 0
|  |  |  | 2.9 | Prepare Business Requirements Document (BRD) | P. Ahmed | Apps | Complete | 100 | Low | No |  | Low | 2026-03-18 | 2026-03-19 | 2026-03-26 | 2026-03-26 | 24 | 24 | 0
Approved Budget | 150000 |  |  | 2.1 | Requirements Sign-Off | J. Park | Apps | Complete | 100 | High | Yes |  | Medium | 2026-03-23 | 2026-03-26 | 2026-04-01 | 2026-04-01 | 33 | 33 | 0
|  | 3 | Design | 3.2 | Solution Design Workshop- SP Tech Internal | T. Bauer | PMO | Complete | 100 | Low | No |  | Low | 2026-03-29 | 2026-03-29 | 2026-04-07 | 2026-04-07 | 80 | 80 | 0
|  |  |  | 3.3 | Solution Design Workshop- W Vendors | A. Silva | Apps | Complete | 100 | Medium | No |  | Medium | 2026-04-03 | 2026-04-04 | 2026-04-12 | 2026-04-12 | 80 | 80 | 0
|  |  |  | 3.4 | Prepare Functional Requirements Document (FRD) | V. Rao | Integration | Complete | 100 | Medium | No |  | Medium | 2026-04-09 | 2026-04-09 | 2026-04-18 | 2026-04-18 | 16 | 16 | 0
|  |  |  | 3.5 | Process Flow Design | R. Mendes | PMO | Complete | 100 | Medium | No |  | Low | 2026-04-15 | 2026-04-15 | 2026-04-23 | 2026-04-23 | 32 | 32 | 0
|  |  |  | 3.6 | Technical Architecture Review | C. Meyer | PMO | Complete | 100 | High | Yes |  | Low | 2026-04-20 | 2026-04-19 | 2026-04-29 | 2026-04-29 | 33 | 33 | 0
|  |  |  | 3.7 | Security & Compliance Review W Security Team | P. Ahmed | Integration | Complete | 100 | Low | No |  | Low | 2026-04-26 | 2026-04-27 | 2026-05-04 | 2026-05-04 | 60 | 60 | 0
|  |  |  | 3.8 | Integration Design | J. Park | PMO | Complete | 100 | Low | No |  | Low | 2026-05-01 | 2026-05-01 | 2026-05-10 | 2026-05-10 | 24 | 24 | 0
|  | 4 | Development | 4.9 | Environment Setup | T. Bauer | Integration | Complete | 100 | Low | No |  | Low | 2026-05-07 | 2026-05-06 | 2026-05-15 | 2026-05-15 | 24 | 24 | 0
|  |  |  | 4.1 | Configuration Activities | A. Silva | Apps | Complete | 100 | Low | No |  | Low | 2026-05-12 | 2026-05-14 | 2026-05-21 | 2026-05-21 | 24 | 24 | 0
|  |  |  | 4.2 | Custom Development (If any) | V. Rao | Integration | Complete | 100 | Medium | No |  | Low | 2026-05-18 | 2026-05-18 | 2026-05-26 | 2026-05-26 | 80 | 80 | 0
|  |  |  | 4.3 | Integration Development | R. Mendes | Apps | Complete | 100 | Medium | No |  | Low | 2026-05-23 | 2026-05-25 | 2026-06-01 | 2026-06-01 | 16 | 16 | 0
|  |  |  | 4.4 | Unit Testing | C. Meyer | Apps | Complete | 100 | Medium | No |  | Low | 2026-05-29 | 2026-05-30 | 2026-06-06 | 2026-06-06 | 60 | 60 | 0
|  | 5 | Testing | 5.5 | Test Plan Preparation | P. Ahmed | Apps | Complete | 100 | Medium | No |  | Low | 2026-06-03 | 2026-06-04 | 2026-06-12 | 2026-06-12 | 60 | 60 | 0
|  |  |  | 5.6 | Testing Steps & Scenarios | J. Park | Integration | Complete | 100 | Medium | No |  | Low | 2026-06-09 | 2026-06-09 | 2026-06-18 | 2026-06-18 | 80 | 80 | 0
|  |  |  | 5.7 | System Testing (SIT) | T. Bauer | PMO | In Progress | 50 | Medium | No |  | Low | 2026-06-14 | 2026-06-15 | 2026-06-23 |  | 60 | 30 | 30
|  |  |  | 5.8 | Integration Testing | A. Silva | Platform | Not Started | 0 | Low | No |  | Low | 2026-06-20 |  | 2026-06-29 |  | 24 | 0 | 24
|  |  |  | 5.9 | QA | V. Rao | PMO | Not Started | 0 | Medium | No |  | Low | 2026-06-26 |  | 2026-07-04 |  | 24 | 0 | 24
|  |  |  | 5.1 | User Acceptance Testing (UAT) | R. Mendes | Platform | Not Started | 0 | High | Yes |  | Low | 2026-07-01 |  | 2026-07-10 |  | 56 | 0 | 56
|  |  |  | 5.2 | UAT Sign Off by Business | C. Meyer | Apps | Not Started | 0 | High | Yes |  | Low | 2026-07-07 |  | 2026-07-15 |  | 22 | 0 | 22
|  | 6 | Implementation | 6.3 | User Training / Demo | P. Ahmed | Integration | Not Started | 0 | Medium | No |  | Low | 2026-07-12 |  | 2026-07-21 |  | 16 | 0 | 16
|  |  |  | 6.4 | User Training | J. Park | Apps | Not Started | 0 | Medium | No |  | Low | 2026-07-18 |  | 2026-07-26 |  | 32 | 0 | 32
|  |  |  | 6.5 | Cutover Planning | T. Bauer | Platform | Not Started | 0 | High | Yes |  | Low | 2026-07-23 |  | 2026-08-01 |  | 33 | 0 | 33
|  |  |  | 6.6 | Go-Live Readiness Review | A. Silva | Platform | Not Started | 0 | High | Yes |  | Low | 2026-07-29 |  | 2026-08-06 |  | 56 | 0 | 56
|  |  |  | 6.7 | GO NO GO Discussion / Approval | V. Rao | Platform | Not Started | 0 | High | Yes |  | High | 2026-08-03 |  | 2026-08-12 |  | 44 | 0 | 44
|  | 7 | Go Live | 7.8 | Production Deployment | R. Mendes | Integration | Not Started | 0 | High | Yes |  | Low | 2026-08-09 |  | 2026-08-17 |  | 44 | 0 | 44
|  |  |  | 7.9 | Hypercare Support | C. Meyer | PMO | Not Started | 0 | Medium | No |  | Medium | 2026-08-14 |  | 2026-08-23 |  | 16 | 0 | 16
|  |  |  | 7.1 | Lessons Learnt | P. Ahmed | Apps | Not Started | 0 | Low | No |  | Low | 2026-08-20 |  | 2026-08-29 |  | 40 | 0 | 40
|  |  |  | 7.2 | Project Closure | J. Park | PMO | Not Started | 0 | Low | No |  | Low | 2026-08-25 |  | 2026-09-03 |  | 32 | 0 | 32
|  |  |  | 7.3 | Post Go Live Support ¦ 4 weeks | T. Bauer | Apps | Not Started | 0 | Medium | No |  | Low | 2026-08-31 |  | 2026-09-09 |  | 60 | 0 | 60