## Project Plan
Project ID | PRJ-0994 | WBS | Phase | Task ID | Project Activity | Owner | Team | Status | % Complete | Priority | Critical path (Yes/No) | Dependency (If any / Predecessors) | Risk Level (Low / Medium / High / Critical) | Planned Start Date | Actual Start Date | Planned Finish Date | Actual Finish date | Effort (hours) | Effort completed (hours) | Effort remaining (hours)
Project Name | Vega Payments Integration | 1 | Initiation | 1.1 | Project Charter | N. Kaur | QA | Complete | 100 | High | Yes |  | Low | 2025-11-10 | 2025-11-12 | 2025-11-19 | 2025-11-20 | 22 | 22 | 0
|  |  |  | 1.2 | Initiation Meeting SP Tech Internal | V. Rao | QA | Complete | 100 | Medium | No |  | Low | 2025-11-16 | 2025-11-19 | 2025-11-26 | 2025-11-26 | 80 | 80 | 0
Planned Go Live Date | 2026-07-25 |  |  | 1.3 | Initiation Meeting W Vendors | H. Costa | Integration | Complete | 100 | Medium | No |  | Low | 2025-11-22 | 2025-11-21 | 2025-12-02 | 2025-12-02 | 24 | 24 | 0
Forcast Go Live Date | 2026-07-29 |  |  | 1.4 | Stakeholder Identification | J. Park | Integration | Complete | 100 | Medium | No |  | Low | 2025-11-28 | 2025-12-01 | 2025-12-08 | 2025-12-09 | 80 | 80 | 0
|  |  |  | 1.5 | Internal & External Meeting Cadence Setup | A. Silva | QA | Complete | 100 | High | No |  | High | 2025-12-05 | 2025-12-07 | 2025-12-15 | 2025-12-15 | 32 | 32 | 0
Project Owner | A. Fischer | 2 | Requirements | 2.6 | Project Kickoff Meeting | E. Novak | Integration | Complete | 100 | Low | No |  | Low | 2025-12-11 | 2025-12-11 | 2025-12-21 | 2025-12-22 | 80 | 80 | 0
Business Stakeholder | Payments & Treasury |  |  | 2.7 | Identify Stakeholders | R. Mendes | QA | Complete | 100 | Medium | No |  | Low | 2025-12-17 | 2025-12-20 | 2025-12-27 | 2025-12-28 | 32 | 32 | 0
Project Manager | R. Mendes |  |  | 2.8 | Gather Business Requirements | N. Kaur | QA | Complete | 100 | Low | No |  | Low | 2025-12-24 | 2025-12-25 | 2026-01-03 | 2026-01-03 | 16 | 16 | 0
|  |  |  | 2.9 | Prepare Business Requirements Document (BRD) | V. Rao | Platform | Complete | 100 | Medium | No |  | Low | 2025-12-30 | 2026-01-01 | 2026-01-09 | 2026-01-10 | 60 | 60 | 0
Approved Budget | 185000 |  |  | 2.1 | Requirements Sign-Off | H. Costa | Integration | Complete | 100 | High | Yes |  | Low | 2026-01-05 | 2026-01-06 | 2026-01-15 | 2026-01-17 | 33 | 33 | 0
|  | 3 | Design | 3.2 | Solution Design Workshop- SP Tech Internal | J. Park | QA | Complete | 100 | Medium | No |  | Medium | 2026-01-12 | 2026-01-11 | 2026-01-22 | 2026-01-23 | 60 | 60 | 0
|  |  |  | 3.3 | Solution Design Workshop- W Vendors | A. Silva | Integration | Complete | 100 | Medium | No |  | Low | 2026-01-18 | 2026-01-17 | 2026-01-28 | 2026-01-29 | 32 | 32 | 0
|  |  |  | 3.4 | Prepare Functional Requirements Document (FRD) | E. Novak | Security | Complete | 100 | Medium | No |  | Medium | 2026-01-24 | 2026-01-24 | 2026-02-03 | 2026-02-04 | 80 | 80 | 0
|  |  |  | 3.5 | Process Flow Design | R. Mendes | Integration | Complete | 100 | Medium | No |  | Low | 2026-01-31 | 2026-02-02 | 2026-02-10 | 2026-02-12 | 16 | 16 | 0
|  |  |  | 3.6 | Technical Architecture Review | N. Kaur | Platform | Complete | 100 | High | Yes |  | Low | 2026-02-06 | 2026-02-09 | 2026-02-16 | 2026-02-17 | 44 | 44 | 0
|  |  |  | 3.7 | Security & Compliance Review W Security Team | V. Rao | QA | Complete | 100 | Low | No |  | Low | 2026-02-12 | 2026-02-14 | 2026-02-22 | 2026-02-25 | 16 | 16 | 0
|  |  |  | 3.8 | Integration Design | H. Costa | Integration | Complete | 100 | Low | No |  | Low | 2026-02-19 | 2026-02-21 | 2026-03-01 | 2026-03-02 | 80 | 80 | 0
|  | 4 | Development | 4.9 | Environment Setup | J. Park | Platform | Complete | 100 | Medium | No |  | Low | 2026-02-25 | 2026-02-26 | 2026-03-07 | 2026-03-09 | 60 | 60 | 0
|  |  |  | 4.1 | Configuration Activities | A. Silva | Platform | Complete | 100 | Low | No |  | Low | 2026-03-03 | 2026-03-04 | 2026-03-13 | 2026-03-15 | 16 | 16 | 0
|  |  |  | 4.2 | Custom Development (If any) | E. Novak | Integration | Complete | 100 | Low | No |  | Low | 2026-03-10 | 2026-03-10 | 2026-03-20 | 2026-03-22 | 40 | 40 | 0
|  |  |  | 4.3 | Integration Development | R. Mendes | Integration | Complete | 100 | Medium | No |  | Low | 2026-03-16 | 2026-03-18 | 2026-03-26 | 2026-03-28 | 60 | 60 | 0
|  |  |  | 4.4 | Unit Testing | N. Kaur | QA | Complete | 100 | Low | No |  | Low | 2026-03-22 | 2026-03-22 | 2026-04-01 | 2026-04-03 | 60 | 60 | 0
|  | 5 | Testing | 5.5 | Test Plan Preparation | V. Rao | Integration | Complete | 100 | Medium | No |  | Low | 2026-03-29 | 2026-03-30 | 2026-04-08 | 2026-04-11 | 40 | 40 | 0
|  |  |  | 5.6 | Testing Steps & Scenarios | H. Costa | Security | Complete | 100 | Low | No |  | Low | 2026-04-04 | 2026-04-05 | 2026-04-14 | 2026-04-16 | 32 | 32 | 0
|  |  |  | 5.7 | System Testing (SIT) | J. Park | QA | Complete | 100 | Medium | No |  | Low | 2026-04-10 | 2026-04-12 | 2026-04-20 | 2026-04-23 | 16 | 16 | 0
|  |  |  | 5.8 | Integration Testing | A. Silva | Security | Complete | 100 | Medium | No |  | Low | 2026-04-17 | 2026-04-18 | 2026-04-27 | 2026-04-30 | 24 | 24 | 0
|  |  |  | 5.9 | QA | E. Novak | QA | Complete | 100 | Medium | No |  | Low | 2026-04-23 | 2026-04-23 | 2026-05-03 | 2026-05-05 | 40 | 40 | 0
|  |  |  | 5.1 | User Acceptance Testing (UAT) | R. Mendes | Platform | Complete | 100 | High | Yes |  | Low | 2026-04-29 | 2026-04-30 | 2026-05-09 | 2026-05-11 | 56 | 56 | 0
|  |  |  | 5.2 | UAT Sign Off by Business | N. Kaur | Platform | Complete | 100 | High | Yes |  | Low | 2026-05-06 | 2026-05-08 | 2026-05-16 | 2026-05-17 | 44 | 44 | 0
|  | 6 | Implementation | 6.3 | User Training / Demo | V. Rao | QA | Complete | 100 | Medium | No |  | Medium | 2026-05-12 | 2026-05-13 | 2026-05-22 | 2026-05-24 | 80 | 80 | 0
|  |  |  | 6.4 | User Training | H. Costa | Security | Complete | 100 | Medium | No |  | Low | 2026-05-18 | 2026-05-19 | 2026-05-28 | 2026-06-02 | 32 | 32 | 0
|  |  |  | 6.5 | Cutover Planning | J. Park | Integration | In Progress | 31 | High | Yes |  | Low | 2026-05-25 | 2026-05-28 | 2026-06-03 |  | 33 | 10 | 23
|  |  |  | 6.6 | Go-Live Readiness Review | A. Silva | Security | Not Started | 0 | High | Yes |  | Low | 2026-05-31 |  | 2026-06-10 |  | 112 | 0 | 112
|  |  |  | 6.7 | GO NO GO Discussion / Approval | E. Novak | Security | Not Started | 0 | High | Yes |  | Low | 2026-06-06 |  | 2026-06-16 |  | 33 | 0 | 33
|  | 7 | Go Live | 7.8 | Production Deployment | R. Mendes | Integration | Not Started | 0 | High | Yes |  | Low | 2026-06-13 |  | 2026-06-22 |  | 33 | 0 | 33
|  |  |  | 7.9 | Hypercare Support | N. Kaur | Security | Not Started | 0 | Medium | No |  | Low | 2026-06-19 |  | 2026-06-29 |  | 80 | 0 | 80
|  |  |  | 7.1 | Lessons Learnt | V. Rao | Platform | Not Started | 0 | Medium | No |  | Low | 2026-06-25 |  | 2026-07-05 |  | 24 | 0 | 24
|  |  |  | 7.2 | Project Closure | H. Costa | Security | Not Started | 0 | Low | No |  | Low | 2026-07-02 |  | 2026-07-11 |  | 32 | 0 | 32
|  |  |  | 7.3 | Post Go Live Support ¦ 4 weeks | J. Park | Integration | Not Started | 0 | Medium | No |  | Low | 2026-07-08 |  | 2026-07-18 |  | 24 | 0 | 24